## general_report
SEF Jira
Displaying 42 issues at 23/Sep/15 1:02 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Rank | Epic Link | Epic/Theme | Sprint | Flagged
IFB299 027 | TWOSEV-50 | Acceptance testing for search via map | Task | Open | Trivial | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-09-16 13:27 | 2015-09-16 13:27 | 2015-09-23 11:30 | [5 empty] | 0 | 1 | [8 empty] | Acceptance testing should be completed for searching for properties using the map. Testing should ensure all properties with valid addresses are shown on the map. | [7 empty] | 0¦ywn1m3: |  |  | Geographical search, contact
IFB299 027 | TWOSEV-49 | Acceptance testing of map view for listings | Task | Open | Trivial | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-09-16 13:24 | 2015-09-16 13:24 | 2015-09-23 11:29 | [5 empty] | 0 | 1 |  | 7200 | 7200 |  | 0% |  |  |  | Acceptance testing must be performed to ensure the operation of the map view for listings. Testing will involve using multiple addresses to ensure accurate location shown on the map. Invalid addresses should also be attempted. |  | 0% | 0% |  | 7200 | 7200 |  | 0¦ywms89:2 |  |  | Geographical search, contact
IFB299 027 | TWOSEV-46 | As a customer I search for property listings using a map so that I can easily identify listings that are appropriate | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-09-16 13:03 | 2015-09-16 15:07 | 2015-09-16 17:33 | [5 empty] | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | Customers should be able to use a map to search for property listings. The map should show the location of all listings simultaneously. See example here: http://www.realestate.com.au/rent/in-brisbane+-+greater+region%2c+qld/map-1 |  | 0% | 0% |  | 28800 | 28800 |  | 0¦ywms89:9 |  |  | Geographical search, contact
IFB299 027 | TWOSEV-45 | Acceptance testing for 'Manage Property Listing' | Task | Closed | Must Have | Fixed | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-09-16 12:53 | 2015-09-16 12:53 | 2015-09-22 11:32 | 2015-09-22 11:32 |  |  |  |  | 0 | 1 |  | 3600 | 1800 | 1800 | 50% |  |  |  | Acceptance testing must be performed on the 'Manage Property Listing' page to ensure it adheres to the same requirements as 'Create Property Listing'. |  | 50% | 50% | 1800 | 1800 | 3600 |  | 0¦ywms96: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-44 | Acceptance Testing for Create Property Listing | Task | Closed | Must Have | Fixed | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-09-16 12:47 | 2015-09-16 12:47 | 2015-09-17 13:30 | 2015-09-17 13:30 |  |  |  |  | 0 | 1 |  | 3600 | 1800 | 1800 | 50% |  |  |  | Acceptance testing must be performed on the 'Create Property Listing' page. Acceptance testing should include a variation of addresses, rental amounts, rental frequencies, number of bathrooms, bedrooms, carports. The acceptance testing should ensure the rent, bathrooms, bedrooms and carport fields only accept numbers. |  | 50% | 50% | 1800 | 1800 | 3600 |  | 0¦ywms95: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-43 | Acceptance Testing for Login | Task | Closed | Must Have | Fixed | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-09-16 12:44 | 2015-09-16 12:44 | 2015-09-17 13:18 | 2015-09-17 13:18 |  |  |  |  | 0 | 2 |  | 3600 | 0 | 3600 | 100% |  |  |  | Acceptance testing to be completed for the login page. Should involve a variation of usernames and passwords. |  | 100% | 100% | 3600 | 0 | 3600 |  | 0¦ywms93: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-42 | As a customer I can contact the administrator via the website so I can conveniently and directly inform them of any inquiries | Story | Reopened | Should Have | Unresolved | Matthew Baker | Matthew Baker | Matthew Baker | 2015-09-02 15:31 | 2015-09-16 12:32 | 2015-09-16 17:37 | [5 empty] | 0 | 1 |  | 3600 | 0 | 3600 | 100% |  |  |  | Customer should be able to contact the administrator via the website by sending email to the administrator so a customer will be able to inform them of any inquiries. |  | 100% | 100% | 3600 | 0 | 3600 |  | 0¦ywms89:5 |  |  | Sprint 1: Core Functionality, Geographical search, contact
IFB299 027 | TWOSEV-40 | As a property manager the website makes my listings look appealing so potential customers can easily view my property information | Story | In Progress | Should Have | Unresolved | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-08-26 15:24 | 2015-09-16 12:32 | 2015-09-23 12:00 | [5 empty] | 0 | 1 | [8 empty] | The website design should appear aesthetically pleasing to customers. | [7 empty] | 0¦ywmsbq:v |  |  | Advanced listing capability
IFB299 027 | TWOSEV-38 | As a property manager I can upload photos to property listing so I can display what my property looks like | Story | In Progress | Should Have | Unresolved | Siu Lun Wong | Matthew Baker | Matthew Baker | 2015-08-26 14:51 | 2015-08-26 14:51 | 2015-09-16 17:44 | [5 empty] | 0 | 1 | [8 empty] | A property manager should be able to upload photos of property to listing for user to see. | [7 empty] | 0¦ywms8q:i |  |  | Advanced listing capability
IFB299 027 | TWOSEV-37 | As a customer I can view a gallery of pictures for a property so I can see different perspectives and angles of the property | Story | In Progress | Should Have | Unresolved | Siu Lun Wong | Matthew Baker | Matthew Baker | 2015-08-26 14:50 | 2015-09-16 12:31 | 2015-09-16 17:44 | [5 empty] | 0 | 1 | [8 empty] | A customer should be able to see some pictures of the property on the webpage. | [7 empty] | 0¦ywms8q:r |  |  | Advanced listing capability
IFB299 027 | TWOSEV-36 | As a customer I can search for a property via its ID number on gumtree so I can view more information about the property on David's website | Story | Resolved | Must Have | Fixed | Unassigned | Matthew Baker | Matthew Baker | 2015-08-26 14:49 | 2015-09-16 12:31 | 2015-09-16 15:50 | 2015-09-09 14:13 |  |  |  | 2015-09-09 | 0 | 1 |  | 36000 | 0 | 1800 | 5% |  |  |  | Gumtree should have a search function which allows customers to easily find properties when entering its ID. |  | 100% | 100% | 1800 | 0 | 36000 |  | 0¦ywms89:0i |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-35 | As a customer I can search for properties near a location using postcode or suburb so I find other properties in the area that I'm interested in | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-26 14:01 | 2015-08-26 15:14 | 2015-09-16 17:31 | [5 empty] | 0 | 1 |  | 120 | 120 |  | 0% |  |  |  | Customers should be able to find results for properties near a given suburb. |  | 0% | 0% |  | 120 | 120 |  | 0¦ywms9n: |  |  | Geographical search, contact
IFB299 027 | TWOSEV-33 | As a customer I can view a webpage detailing a property so I can see more information about a property and whether it is suitable for me | Story | Closed | Must Have | Fixed | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 16:04 | 2015-08-26 14:26 | 2015-09-16 17:31 | 2015-09-16 17:31 |  |  |  | 2015-09-09 | 0 | 1 |  | 18000 | 0 | 86400 | 480% |  |  |  | Customers should be able to view the details of a property on a webpage. The webpage should display the information of a property to the customer. |  | 100% | 100% | 86400 | 0 | 18000 |  | 0¦ywms76: |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-32 | As an administrator I have discretionary user access control so I can change the permissions of users | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:53 | 2015-08-26 15:27 | 2015-09-16 17:30 | [5 empty] | 0 | 1 | [8 empty] | An administrator should be able to do everything a property manager can do such as listing contact details and editing the property information. | [7 empty] | 0¦ywmslv: |  |  | PM account implementation
IFB299 027 | TWOSEV-31 | As a property manager I can change the way the website notifies me from email to SMS so I can receive notifications in which ever method I prefer | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:53 | 2015-08-19 16:00 | 2015-09-16 17:38 | [5 empty] | 0 | 1 |  | 14400 | 14400 |  | 0% |  |  |  | A property manager can be able to change the way of notifications from email to SMS to provide different preferences of notifications for them |  | 0% | 0% |  | 14400 | 14400 |  | 0¦ywmsm2: |  |  | PM account implementation
IFB299 027 | TWOSEV-29 | As a property manager I can assign tenant information to a property listing causing the listing to no longer be visible to customers so customers cannot contact me regarding a property that is no longer available | Story | In Progress | Must Have | Unresolved | Mitchell Sainty | Matthew Baker | Matthew Baker | 2015-08-19 15:50 | 2015-08-19 15:51 | 2015-09-17 13:41 | [5 empty] | 0 | 1 |  | 14400 | 14400 |  | 0% |  |  |  | A property manage should be able to view the contact details for tenants in order to provide communication between tenants and property owner. |  | 0% | 0% |  | 14400 | 14400 |  | 0¦ywmsbq: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-28 | As an administrator I can take the website offline so I perform maintenance on the website | Story | Resolved | Should Have | Fixed | Matthew Baker | Matthew Baker | Matthew Baker | 2015-08-19 15:43 | 2015-09-02 15:35 | 2015-09-16 15:47 | 2015-09-02 15:35 |  |  |  |  | 0 | 1 |  | 36000 | 0 | 7200 | 20% |  |  |  | The website is available offline for the administrator and can be altered or changed to the administrators liking |  | 100% | 100% | 7200 | 0 | 36000 |  | 0¦ywms6k: |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-27 | As an administrator I can see a view count for each property listing so I can see the popularity of properties | Story | Closed | Should Have | Fixed | Matthew Baker | Matthew Baker | Matthew Baker | 2015-08-19 15:42 | 2015-09-22 13:20 | 2015-09-22 13:20 | 2015-09-22 13:19 |  |  |  |  | 0 | 1 |  | 240 | 0 | 14400 | 6000% |  |  |  | The administrator should be able to send a user an email, showing interest in the house or property |  | 100% | 100% | 14400 | 0 | 240 |  | 0¦ywms97: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-26 | As an administrator I can view/upadate/delete all details of tenants currently assigned to all properties so I can assist users in performing these functions | Story | In Progress | Should Have | Unresolved | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-08-19 15:42 | 2015-08-26 15:14 | 2015-09-23 11:49 | [5 empty] | 0 | 1 |  | 120 | 120 |  | 0% |  |  |  | The administrator should be able to see the contact information including the email, phone number and possibly a Facebook link, to be able to easily contact the user or customer |  | 0% | 0% |  | 120 | 120 |  | 0¦ywmsb1: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-25 | As an administrator I can blacklist usernames so I can disallow usernames containing offensive words | Story | Open | Won't Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:41 | 2015-08-26 15:29 | 2015-09-16 17:28 | [5 empty] | 0 | 1 |  | 300 | 300 |  | 0% |  |  |  | If a user is hacking or using the website in the wrong manner, the administrator should be able to block the user from accessing the website or adding any properties to the website |  | 0% | 0% |  | 300 | 300 |  | 0¦ywmsm9: |  |  | PM account implementation
IFB299 027 | TWOSEV-24 | As an administrator I can update user accounts so I can assist users in changing their information | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:41 | 2015-08-19 15:41 | 2015-09-16 17:28 | [5 empty] | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | An administrator can edit user account details and delete users if needed. A banned user may be deleted by the administrator. |  | 0% | 0% |  | 28800 | 28800 |  | 0¦ywmsbr: |  |  | PM account implementation
IFB299 027 | TWOSEV-23 | As an administrator I can delete user accounts so I can remove users who are breaching the terms of service | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:40 | 2015-08-19 15:56 | 2015-09-16 17:27 | [5 empty] | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | If users abuse their account and violate the policy, their accounts may be banned by the administrator. |  | 0% | 0% |  | 28800 | 28800 |  | 0¦ywmsbs: |  |  | PM account implementation
IFB299 027 | TWOSEV-22 | As an administrator I can create,update and delete all listings so I can assist property managers in performing these functions | Story | Resolved | Must Have | Fixed | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:40 | 2015-09-16 12:34 | 2015-09-16 15:41 | 2015-09-16 12:34 |  |  |  | 2015-09-23 | 0 | 1 |  | 43200 | 43200 | 3600 | 8% |  |  |  | An administrator can edit and update pages of property on the webpage at any time |  | 7% | 7% | 3600 | 43200 | 43200 |  | 0¦ywms8o: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-20 | As an administrator my log in will time out if I am inactive for a long period of time so my account won't be used for unauthorized activity | Story | In Progress | Could Have | Unresolved | Daniel Bogaart | Matthew Baker | Matthew Baker | 2015-08-19 15:38 | 2015-08-26 15:26 | 2015-09-23 12:00 | [5 empty] | 0 | 1 |  | 36000 | 36000 |  | 0% |  |  |  | A property manager should easily be able to be contacted by anyone, including users, customers, other property managers and admins. |  | 0% | 0% |  | 36000 | 36000 |  | 0¦ywmsbt: |  |  | Advanced listing capability
IFB299 027 | TWOSEV-19 | As an administrator I can have root access to the website so that I can resolve unforeseen issues | Story | Reopened | Must Have | Unresolved | Matthew Baker | Matthew Baker | Matthew Baker | 2015-08-19 15:37 | 2015-09-02 15:34 | 2015-09-16 15:36 | [5 empty] | 0 | 1 |  | 36000 | 0 | 28800 | 80% |  |  |  | An administrator should be able to add new page of information to the webpage |  | 100% | 100% | 28800 | 0 | 36000 |  | 0¦ywms6j:9 |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-18 | As a Customer I can request an inspection so I can arrange a time to inspect the property | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:37 | 2015-08-19 15:37 | 2015-09-16 17:38 | [5 empty] | 0 | 1 |  | 36000 | 36000 |  | 0% |  |  |  | Communication can be done with interested customers to come and inspect the property. |  | 0% | 0% |  | 36000 | 36000 |  | 0¦ywms89:3 |  |  | Geographical search, contact
IFB299 027 | TWOSEV-17 | As a property manager my details are assigned to my listings automatically so I can be contacted by potential customers | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:36 | 2015-08-19 15:36 | 2015-09-16 17:25 |  |  |  |  | 2015-09-23 | 0 | 1 |  | 21600 | 21600 |  | 0% |  |  |  | A property manager should be able to list contact details of property owner on the listing for tenants to contact them. |  | 0% | 0% |  | 21600 | 21600 |  | 0¦ywms8z: |  |  | PM account implementation
IFB299 027 | TWOSEV-16 | As a customer I can compare two properties so I can see the similarities and differences between them | Story | Open | Could Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:33 | 2015-08-26 14:53 | 2015-09-23 11:28 | [5 empty] | 0 | 1 |  | 108000 | 108000 |  | 0% |  |  |  | A customer should easily be able to see the differences in features between two properties such as their price, area, number of bedrooms, bathrooms and garages. |  | 0% | 0% |  | 108000 | 108000 |  | 0¦ywms8h: |  |  | PM account implementation
IFB299 027 | TWOSEV-15 | As a customer I can contact the agent managing a property via the website so I can conveniently and directly inform them of any inquiries | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:33 | 2015-08-26 15:07 | 2015-09-16 17:38 |  |  |  |  | 2015-09-23 | 0 | 1 |  | 36000 | 36000 |  | 0% |  |  |  | A customer should be easily able to view a managing agent's details and contact the agent via the site. |  | 0% | 0% |  | 36000 | 36000 |  | 0¦ywms89:7 |  |  | Geographical search, contact
IFB299 027 | TWOSEV-14 | As a customer I can see recommendations based of previous searches so I am informed of similar properties which are suitable for me | Story | Open | Could Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:32 | 2015-08-26 14:53 | 2015-09-16 15:35 | [5 empty] | 0 | 1 |  | 180000 | 180000 |  | 0% |  |  |  | The customer should be given recommendations of similar properties of interest in terms of pricing, location, area, etc. |  | 0% | 0% |  | 180000 | 180000 |  | 0¦ywmsbv: |  |  | Geographical search, contact
IFB299 027 | TWOSEV-13 | As a property manager I can use my account to delete listings for properties assigned to me so customers cannot contact me regarding a property that is no longer available | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:31 | 2015-08-26 15:13 | 2015-09-16 17:24 |  |  |  |  | 2015-09-23 | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | Property managers should be able to remove their listings at any time for any reason. |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywms8q: |  |  | PM account implementation
IFB299 027 | TWOSEV-12 | As a property manager, I can use my account to edit listings for properties assigned to me so I don't need to delete the listing and create a new listing | Story | Open | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:30 | 2015-08-19 15:30 | 2015-09-16 17:24 |  |  |  |  | 2015-09-23 | 0 | 1 |  | 86400 | 86400 |  | 0% |  |  |  | The property manager should be able to change the details of listings such as price, location and contact information. |  | 0% | 0% |  | 86400 | 86400 |  | 0¦ywmsar: |  |  | PM account implementation
IFB299 027 | TWOSEV-11 | As a property manager, I can use my account to create listings so I can advertise my property for rent | Story | Reopened | Must Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:30 | 2015-08-19 15:30 | 2015-09-16 17:23 |  |  |  |  | 2015-09-09 | 0 | 1 |  | 28800 | 0 | 144000 | 500% |  |  |  | If you are logged in to the website, you should be able to add a house with prices, photos, no. of bedrooms/bathrooms/garages, etc. |  | 100% | 100% | 144000 | 0 | 28800 |  | 0¦ywms6n: |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-10 | As a property manager my log in will time out if I am inactive for a long period of time so my account won't be used for unauthorised activity | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:30 | 2015-08-26 15:11 | 2015-09-16 17:22 | [5 empty] | 0 | 1 |  | 43200 | 43200 |  | 0% |  |  |  | A login/register button needs to be available for viewing on the home screen to make it as easy as possible to sign up |  | 0% | 0% |  | 43200 | 43200 |  | 0¦ywms8a: |  |  | PM account implementation
IFB299 027 | TWOSEV-6 | As a customer I can search for a property based on number of bedrooms and/or number of carports and/or rent price and/or number of bathrooms and/or address and/or rental frequency | Story | Resolved | Should Have | Fixed | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:26 | 2015-09-16 12:33 | 2015-09-16 15:26 | 2015-09-16 12:33 |  |  |  |  | 0 | 1 |  | 36000 | 0 | 1800 | 5% |  |  |  | A customer should be able to refine their search by the number of bathrooms a property has. |  | 100% | 100% | 1800 | 0 | 36000 |  | 0¦ywms89:0v |  |  | Advanced listing capability
IFB299 027 | TWOSEV-3 | As a customer I want to view the details of property I have chosen to view to see if its features are suitable so that I can rent the property | Story | Closed | Must Have | Fixed | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 15:22 | 2015-08-19 16:07 | 2015-09-16 17:19 | 2015-09-16 17:19 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 28800 | 266% |  |  |  | Customers should be able to see the listed price for properties |  | 100% | 100% | 28800 | 0 | 10800 |  | 0¦ywms7n: |  |  | Sprint 1: Core Functionality
IFB299 027 | TWOSEV-1 | As a customer I can view properties location on a map so I can see nearby roads, shops, parks and other local places of interest | Story | Open | Should Have | Unresolved | Unassigned | Matthew Baker | Matthew Baker | 2015-08-19 14:38 | 2015-08-19 16:03 | 2015-09-16 17:18 |  |  |  |  | 2015-09-23 | 0 | 1 |  | 72000 | 72000 |  | 0% |  |  |  | A user should be able to see the location of a listing they are viewing on a map. |  | 0% | 0% |  | 72000 | 72000 |  | 0¦ywms89:1 |  |  | Geographical search, contact
Generated at Wed Sep 23 13:02:08 EST 2015 by Matthew Baker using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.